## 90-Day Planner
90-Day Roadmap Planner
Week-by-week, with pre-filled milestones. The ultimate 'do this Monday' tool.
AI COMPASS · Bonus Tool · book.aicompass.ai
Week | Phase | Pre-filled milestones (edit freely) | Owner | Status | Notes
Week 1 | Phase 1 · Foundation | Leadership alignment session (half-day). Name ONE executive sponsor. Write 90-day success definition (one measurable sentence). Confirm budget envelope. Deploy enterprise AI tools (SSO, 'training off'). Publish one-page AI policy + Traffic-Light Protocol. |  | Not started
Week 2 | Phase 1 · Foundation | Scorecard Workshop: inventory 40-60 opportunities, calibrate scoring, plot Value vs Complexity. Select 3-5 Quick Wins + 1-2 Strategic Bets with owners. Set 30-day (QW) and 90-day (bet) milestones. |  | Not started
Week 3 | Phase 1 · Foundation | Champion Activation: select 5-10 champions (credible, curious, connected). Train them on tools + role. Launch the network, weekly 30-min sync, shared channel. |  | Not started
Week 4 | Phase 1 · Foundation | Organisation-wide fluency: mandatory 2-hr all-hands AI training. Launch 'AI Office Hours' (2-3/week, drop-in). Day 29-30 Phase-1 review; confirm Quick Win priorities. |  | Not started
Week 5 | Phase 2 · Traction | Quick Win execution begins. Owners implement; champions support; optional 15-min daily standups. Aim: ship first Quick Win by Day 35 - celebrate it publicly. |  | Not started
Week 6 | Phase 2 · Traction | Second & third Quick Wins ship (~Day 42). Measure & document time saved. Share success stories internally; collect user feedback. |  | Not started
Week 7 | Phase 2 · Traction | Workflow standardisation: champions document best prompts, build reusable templates, start the Skill Library, define 'what good looks like'. |  | Not started
Week 8 | Phase 2 · Traction | Cross-functional 'Show & Tell' - each function shares its best workflow. Strategic Bet owner finalises the detailed plan; leadership Go/No-Go review (Day 57-60). |  | Not started
Week 9 | Phase 3 · Acceleration | Strategic Bet kickoff (Day 61-63): full team, clear roles, comms plan, first sprint goals. Quick Wins keep scaling. |  | Not started
Week 10 | Phase 3 · Acceleration | Strategic Bet execution (Day 64-75): weekly progress reviews, blocker escalation to sponsor, share early/partial results. |  | Not started
Week 11 | Phase 3 · Acceleration | Institutionalisation: refine governance from 60+ days of edge cases. Expand Skill Library to 30-50 templates with version control. |  | Not started
Week 12 | Phase 3 · Acceleration | Measurement & reporting (Day 85-88): compile 90-day results, ROI calc. Day 89-90 leadership checkpoint + board report. Confirm next 90-day priorities. |  | Not started

## 90-Day Checklist
The 90-Day Checklist
Check this list weekly. Tick the box as each item completes.
AI COMPASS · Bonus Tool · book.aicompass.ai
Phase 1 · Foundation (Days 1-30)
Done | Item | Owner
Leadership alignment session completed
Executive sponsor named
90-day success definition written
Enterprise AI tools deployed
One-page AI policy published
Scorecard workshop completed
3-5 Quick Wins selected with owners
1-2 Strategic Bets identified
5-10 champions trained
All-hands training completed
Office hours running
Phase 2 · Traction (Days 31-60)
Done | Item | Owner
First Quick Win shipped
3-5 Quick Wins live
Time savings measured
Success stories shared
Skill Library started (10-20 templates)
Cross-functional sharing completed
Strategic Bet plan approved
Phase 3 · Acceleration (Days 61-90)
Done | Item | Owner
Strategic Bet launched
Skill Library expanded (30-50 templates)
Governance refined based on experience
90-day results compiled
Board report prepared
Next 90-day priorities confirmed

## Week 1 Trigger
Do This Now: 3 Calendar Invites
If you do only one thing this week, send these three invites. The calendar is the commitment.
AI COMPASS · Bonus Tool · book.aicompass.ai
# | Meeting | When | Attendees
1 | Leadership Alignment Session (half-day) | Day 1-2 | Executive team
2 | Scorecard Workshop (half-day) | Week 2-3 | Function heads + potential champions
3 | 90-Day Review (half-day) | Day 89-90 | Leadership checkpoint